Гуманитарный проект

учреждения «Краснопольский районный центр социального обслуживания населения»

| - Название проекта «Праздник в каждый дом» |  |  |  |
| --- | --- | --- | --- |
| - Срок реализации проекта: 12 месяцев |  |  |  |
| - Организация – заявитель, реализующая гуманитарный проект: учреждение «Краснопольский районный центр социального обслуживания населения» |  |  |  |
| - Цель: организация поздравлений для граждан, находящихся в трудной жизненной ситуации |  |  |  |
| - Задачи: организация и реализация в доступной форме поздравлений для граждан, находящихся в трудной жизненной ситуации, проживающих на территории Краснопольского района, приобщение к лучшим образцам национальной и мировой культуры, организация досуга населения на высоком уровне |  |  |  |
| - Целевая группа: граждане, находящиеся в трудной жизненной ситуации, проживающие на территории Краснопольского района |  |  |  |
| - Краткое описание мероприятий в рамках проекта: |  |  |  |
| Перечень мероприятий (количественные показатели) | Ожидаемые результаты |  | Срок реализации |
| Мероприятие 1. Подбор, закупка костюмов, приобретение звукового оборудования, приобретение атрибутов для организации поздравлений, создание банка музыкального репертуара | создание условий для организации праздничных поздравлений |  | 1-2 месяц |
| Мероприятие 2. Разработка и изготовление информационных материалов о реализации проекта; размещение и распространение информационных материалов в СМИ, среди населения района | информирование населения о реализации проекта |  | 3 месяц |
| Мероприятие 3. Организация поздравлений | организация поздравлений |  | 3-12 месяц |
| - Общий объем финансирования (в долларах США) |  |  |  |
| Источник финансирования |  | Объем финансирования |  |
| Средства донора |  | 2000 |  |
| Софинансирование |  | 620 |  |
| - Место реализации проекта (область/район, город): Республика Беларусь, Могилевская область, г.п. Краснополье, ул. Ленинская, д. 2 |  |  |  |
| - Контактное лицо: ФИО: Конопля Марина Николаевна Должность: психолог, отделение первичного приема, оценки нуждаемости в социальной поддержке и комплексной поддержки в кризисной ситуации учреждения «Краснопольский районный центр социального обслуживания населения» Телефон: +375223871228, +375447543332 Адрес электронной почты: konoplya.mn@mintrud.by |  |  |  |

Humanitarian project

Institution "Krasnopolsky District Center for Social Services"

| - The name of the project is "Holiday in every home" |  |  |  |
| --- | --- | --- | --- |
| - The project implementation period: 12 months |  |  |  |
| - The applicant organization implementing a humanitarian project: the institution “Krasnopolsky District Center for Social Services for the Population” |  |  |  |
| - Purpose: organizing congratulations for citizens who are in a working life situation. |  |  |  |
| - Objectives: organizing and implementing congratulations in an accessible form for citizens in difficult life situations living in the Krasnopolsky district; familiarization with the best examples of national and world culture; organization of leisure time for the population at a high level |  |  |  |
| - Target group: citizens in difficult life situations living in the Krasnopolsky district |  |  |  |
| - Brief description of activities within the project: |  |  |  |
| List of activities (quantitative indicators) | Expected results |  | Implementation period |
| Activity 1. Selection and purchase of costumes, purchase of sound equipment, purchase of attributes for organizing congratulations, creation of a bank of musical repertoire | creating conditions for organizing holiday greetings |  | 1-2 month |
| Activity 2. Development and production of information materials about the implementation of the project; placement and distribution of information materials in the media, among the population of the region | informing the population about the project implementation |  | 3 month |
| Activity 3. Organization of congratulations | organization of congratulations |  | 3-12 month |
| - Total funding (in US dollars) |  |  |  |
| Source of funding |  | Amount of funding |  |
| Donor funds |  | 2000 |  |
| Co-financing |  | 620 |  |
| - Place of project implementation (region/district, city): Republic of Belarus, Mogilev region, urban settlement. Krasnopolye, st. Leninskaya, 2 |  |  |  |
| - Contact person: Full name: Marina Nikolaevna Konoplya Position: psychologist, the department for initial intake, assessment of the need for social support, and comprehensive support in crisis situations of the institution “Krasnopolsky District Center for Social Services of the Population” Phone: +375223871776, +375447543332 Email address: konoplya.mn@mintrud.by |  |  |  |